## Sheet1
Project Name | Accountable Group/Person | Central Grid ref. | Water body ID | Site/Reach/Subcatchment | Project Outline (inc km enhanched) | Additional Benefits to people and environment | Catchment Priority | [7 empty] | Status | Delivery timescale | Estimated cost | Comments | Funded | Funding Source | Monitoring Plan
[7 empty] | Pollution (agri/pesticide) | Pollution Urban | Habitat Improvement | Fish Passage | Citizen Science | Species (recovery/tackling invasive) | NFM | Protected Area/Site
Hoo mill weir removal | SWT | SJ9950024002 | GB104028053272 | Trent source to sow | Project to remove a box culvert on the River Trent at Hoo Mill near great Haywood (SJ9950024002). This will increase daylight in the river, improve fish passage and habitat diversity in the area.The bridge is formed from a box culvert the invert of which forms the weir. The preferred option, if feasible is to remove the entire weir. The current landowner is in agreement to remove the weir. Hoo Mill is less than 300m from the HS2 rail line. Significant money has been spent in the past constructing and maintaining a rock ramp but this remains unsatisfactory and will require ongoing maintenance therefore removal would be the best solution. | [9 empty] | Aspirational |  | 95000 | HS2 possibility | No | HS2
Restoring the Penk (Whiston brook) | SWT | SJ844132 | GB104028046761 | Whiston Brook | Project to address agricultural diffuse pollution and improve river habitat through a combination of advice and guidance and capital works including rural SuDS projects, fencing off water courses, creating cattle drinking bays and riparian tree planting. | [9 empty] | Ongoing | 2016 - 2020 | 150000 |  | EA | WEG
Farming Floodplains for the Future/Saving Our Sow © N.Mott | SWT | SJ8123729707 | GB104028052990 | Upper Sow | Reducing flood risk, addressing agricultural diffuse pollution and improving river habitat on the River Upper Sow/Meece Brook, focusing on Priority Sites (Copmere & Doxey), working with the local flood action group, Facilitation Fund application 2018. | [9 empty] | Aspirational | 2016 - 2020 | 150000 | Phase 1 completed, looking for opportunities to continue this work. Estimated expenditure year on year, includes cost for project post | WEG & Facilitation Fund | WEG Facilitation Fund
NFM /Restoring the Scotch Brook | SWT | SJ 9063434418 | GB104028046761 | Scotch Brook | Installing natural flood management schemes at strategic locations to reduce flood risk in Stone combination with addressing rural diffuse pollution and improving river habitat. | [9 empty] | Ongoing | 2017 - 2020 | 150000 | Estimated expenditure year on year | SCC for NFM & WEG
Trent Headwaters | SWT |  |  |  | Carrying out river restoration opportunities in the Trent Headwaters - improving morphology, habitat and water quality | [9 empty] | Aspirational |  | £100,000-£200,000 | Estimated expenditure year on year | No
Protecting Blithfield resevoir | SSW | SK0541524169 | GB30435478 | Subcatchment | Reducing nutrients and pesticides into Blithfield reservoir through farmer engagement and provision of advice on best practice and management. Access to all farmers in the Blite Catchment to funding through the SPRING2 scheme offered by South Staffs Water | Drinking water quality improvement | [8 empty] | Ongoing |  | 200000 | Estimated expenditure year on year | Funded | South Staffs Water
Trent Valley improvements | TTTV |  |  |  | Carrying out river restoration opportunities and creating a network of blue green infrastructure across the Trent Valley linking up with ERDF and HLF projects | [11 empty] | 100000 | Estimated expenditure year on year | Pending | HLF in development phase
Crayfish Conservation | SWT |  |  |  | Raising awareness of the species and promoting research link opportunities with Universities, secure improved biosecurity at key sites, maintain the spring fed hatchery and continuation of the Ark sites at Cannock Chase, AONB & SAC. Protection of the last Crayfish SSSI at Walk Mill, Cannock. | [11 empty] | 20000 | Estimated expenditure year on year | No
SUNRISE - SuDS Retrofit | Groundwork West Midlands | Various throughout the city of Stoke on Trent | GB104028053360 GB104028053271 GB104028053301 |  | Retrofitting a range of SuDs options at strategic locations throughout the city of Stoke on Trent, in order to reduce the risk of flooding | [9 empty] | Ongoing | March 2018 - 2020 | 298891 |  | Funded | ERDF 60% & Local Levy Fund
SUNRISE - Etruria Valley | SOTCC |  | GB104028053360 | Fowlea Brook | Improvements to the Fowlea brook river corridor through Etruria Valley, Stoke-on-Trent. The project will create a seasonal wetland to store flood water that in combination with works further downstream will reduce flood risk to properties. The work will incorporate environmental enhancements to improve the morphology and water quality of the Fowlea brook. | [9 empty] | Awaiting delivery | Jul 2018 - Sept 2020 | 1415000 |  | Funded | ERDF 60% & SOTCC
SUNRISE - Silverdale Country Park | Groundwork West Midlands | SJ809472 | GB104028053340 | Lyme Brook | Pond creation and removal of invasive species | [9 empty] | Awaiting delivery | Apr 18 - Sept 2020 | 41692 |  | Funded | ERDF 60% & Groundwork West Midlands
SUNRISE - Pool Dam Marsh/Lyme Brook | SWT | SJ837462 | GB104028053340 | Lyme Brook | Re-route the brook into its old channel which should create flow diversity and morphological diversity. Restoration of ditches through vegetation clearance to hopefully re-wet sections of the site. Introduction of water control structures to prevent seasonal drying out of the site which should provide conditions suitable for a more diverse range of species. Restoration of waterbodies. Management of bankside trees which will include thinning and pollarding where appropriate | [9 empty] | Awaiting delivery | Jan - Sept 2019 | 56675 |  | Funded | ERDF 60% & Newcastle Borough Council
SUNRISE - Bradwell/Fowlea Brook | SWT | SJ842504 | GB104028053360 | Fowlea Brook | Installation of woody debris into the watercourses to diversify flow patterns and attempt to trap some of the sediments before reaching the pools and the downstream parts of the Fowlea Brook. Rotational coppicing and/or thinning of trees along the brook corridor to diversify light/shade regime. Possible de-silting of the two large pools and some rotational coppicing of the surrounding trees to provide a better light/shade regime. | [9 empty] | Awaiting delivery | Oct 18 - Mar 2020 | 40000 | Inc woodland costs | Funded | ERDF 60%
SUNRISE - Lyme Brook | SWT | SJ854449 | GB104028053340 | Lyme Brook | Removal of weir/creation of rock ramp to tackle issues with sewage pipe spanning the brook (SJ857441) and enabling better fish passage throughout the reach. Invasive species control. Conversations have been had with Severn Trent who's asset this is and they are in support of the project. | Supporting the ongoing work with GWWM and the Love your Rivers project and Lyme Brook Friends Group | [8 empty] | Awaiting delivery | Jul 2018 - Sept 2020 | 30800 | Inc woodland costs | Funded | ERDF 60%
SUNRISE - Victoria Ground, Stoke-on-Trent | SWT | SJ872432 | GB104028053271 | Reach - River Trent | Creation of a new naturalised river channel on the eastern boundary of the site, improving the diversity of river morphology and increasing flow. The project will increase marginal and in channel aquatic plants and include removal/modification of weirs to improve fish passage particularly for brown trout. This section of the trent is one of the last remaining barriers to fish movement on the Trent. As part of the new river channel cycle way and footpath will be constructed which will link with the existing public rights of way network across the city. | [9 empty] | Awaiting delivery | Oct 18 - Sept 2019 | 900000 |  | Funded | ERDF 60% & SOTCC
SUNRISE - Staffordshire University | WTT | SJ886456 | GB104028053301 | Trent | Possibly re-meander the river channel to diversify pool and riffle flow structure. Digging out new channels and backfilling existing sections, further creation of backwaters and seasonal inundation areas will provide increased water storage capacity in times of high flow as well as providing increased habitat diversity. If the option above is not feasible then implementation of soft engineering techniques such as installation of in stream structures (woody debris, engineered log jams etc.) to sort substrates and diversify flow patterns at several locations throughout the length of the watercourse. Possible removal of the armoured stone toe of the riverbank to allow the river to increase erosion and deposition rates leading to a more ‘natural’ channel. | [9 empty] | Awaiting delivery | Jul 2019 - Jun 2020 | 107000 | Inc grassland cost | Funded | ERDF 60%
SUNRISE - Trent Mill | SWT | SJ893472 | GB104028053301 | Trent | Re-design of culvert and rock ramp to secure better watercourse connection and fish passage. Protect existing and add additional woody debris through keying and hinging in trees providing more aquatic refuge. Planting of Willow whips on the right hand bank to promote channel re-naturalisation as well as installation of an engineered log jam to provide fish habitat and protect the weak bank by the bridge. Lowering of riverbed downstream of the bridge to reduce sediment impoundment. Address fish passage issues at weir. | [9 empty] | Awaiting delivery | Apr 2020 - Sept 2020 | 53000 |  | Funded | ERDF 60%
SUNRISE - Bucknall Park | SWT | SJ899474 | GB104028053301 | Trent | Installation of woody debris and brushwood berms into the channel of the River Trent to further diversify flow and provide additional species habitat. Introduce gravels into the channel of the River Trent to provide flow diversity and potentially new sites for fish spawning. Protect and enhance existing beneficial features such as tree root bundles and fallen trees by pinning or anchoring in place. Divert the brook on the eastern edge of the site through the existing area of wet grassland to provide additional ‘natural’ habitat. | [9 empty] | Awaiting delivery | Jul 2019 - Sept 2019 | 55000 |  | Funded | ERDF 60%
SUNRISE - Cromer Road | SWT | SJ899481 | GB104028053301 | Trent | Removal of inchannel contruction acting as a barrier to fish passage. Introduction of woody material into the channel will help to trap fine sediments leading to the diversification of flow patterns, provide additional habitat for fish and other species and encourage natural deviation in the channel. Creation of a cluster of 5 - 10 shallow ponds throughout the areas of wet grassland, which may be subject to seasonal drying out every 2 - 3 years, to provide additional supporting habitat for the riparian zone. | [9 empty] | Awaiting delivery | Aug 2018 - Oct 2018 | 108400 |  | Funded | ERDF 60%
SUNRISE - Milton | SWT | SJ902504 | GB104028053400 | Trent | Possibly re-meander the river channel to diversify pool and riffle flow structure. Digging out new channels and backfilling existing sections, further creation of backwaters and seasonal inundation areas will provide increased water storage capacity in times of high flow as well as providing increased habitat diversity. If the option above is not feasible then implementation of soft engineering techniques such as installation of in stream structures (woody debris, engineered log jams etc.) to sort substrates and diversify flow patterns at several locations throughout the length of the watercourse. In conjunction with the above, rotational tree management through coppicing and thinning will improve light/shade regime for the watercourse, as well as providing material for which to create in-stream habitat improvement structures. | [9 empty] | Awaiting delivery | Jul 2019 -Dec 2019 | 27450 |  | Funded | ERDF 60%
SUNRISE - Causley Brook | SWT | SJ907469 | GB104028053310 | Reach | Rotational coppicing of trees to provide a more beneficial light/shade regime along the course of the brook. Felled material can be used to create additional woody debris in the brook channel to aid in the sorting of sediments into particle sizes. Removal/modification of weirs, improved stream morphology. Control of invasive Himalayan Balsam along the banks of the watercourse. | [9 empty] | Awaiting delivery | Apr 2018 - Sept 2020 | 79300 | Inc grassland cost | Funded | ERDF 60%
SUNRISE - Ford Green Brook | SWT | SJ890504 | GB104028053380 | Reach | Periodic vegetation clearing from settlement/balancing ponds to maintain some open water. Bank re-profiling and rotational tree felling/thinning alongside the watercourses to improve the light/shade regime south of the A53. Introduction of woody material to the brook channel to encourage the brook to meander naturally. Material could be sourced from any on-site woodland management activities. The use of Natural Flood Management techniques to slow the flow and improve habitat to the brook through Chatterley Whitfield. Enhancement to Ford Green Reedbed by controlling water levels and planting additional reeds. Creation of additional wetland on amenity grassland adjacent to Ford Green Reedbed. | Prevent flooding at Ford Green Hall, improve availability of amenity area for visitors | [8 empty] | Awaiting delivery | Jul 2019 - Dec 2019 | 55065 |  | Funded | ERDF 60%
Tad Brook Meander | South Staffs Water | SK05947261 | GB104028046520 | Tad Brook | Tad Brook has been canalised along it's length and is a highly modified watercourse. The project aims to re-naturalise a 300m length to create a meander into adjacent wet woodland. Area is within a Drinking Water protection zone and would be an extension to the work carried out by the Blithfield Pesticides Group. It would improve the Brook for Ivertebrates Macro and Fish. | [9 empty] | Aspirational | 2018 -2020 | 16690 |  | No | WEG (applied for)
Love your River - Lyme Brook, Moat Brook and River Penk | Groundwork West Midlands | Various across the 3 water courses | Various | Lyme Brook, Moat Brook & River Penk | Advisory report carried out by the Wild Trout Trust making a number of recommendations across the target watercourses. These recommendations will be taken forward in the form of a number of water course enhancements focusing on soft engineering works in areas that have been subject to artificial changes in the past. Activities will be carried out with volunteers supported by Wild Trout Trust and Groundwork West Midlands. Alongside these practical enhancements GWWM will deliver a range of educational activities within communities surrounding the watercourses. | [9 empty] | Ongoing | 2016 - 2020 |  |  | Part funded for some delivery, looking for more | WEG
HS2 Mitigation |  |  |  | HS2 Corridor | 20km away from line …… waiting updated version